Weeley Parish Council

Clerks Report – 22nd April 2025

|  | Topic | Action/issue | Information | Status |
| --- | --- | --- | --- | --- |
|  | Scout Hut | Prepare a new lease. | Have initiated a chat with a new solicitor from Sparlings and have sent a copy of the lease to them. Awaiting response before contacting the Scouts. It is proposed to make the lease 35 years. Estimate received for creating a new lease but also with some information for the Scouts to be passed onto them. Scouts have now appointed representation. | Met with the Scouts along with Cllr Hamilton and have made the final statements known to our solicitor and hopefully this will now complete very soon. |
|  | Weeley bypass | Determine options for the avenue of poplars | The Clerk has agreed to contact ECC Place Services to chase for a firm proposal including numbers and species of trees to plant. | Email received from ECC Place Services with suggestions. Postponing until March meeting as December meeting is very busy currently. |
|  | Reed Pond | Initiate Management Plan | - Obtain costs to install a chlorine pump - Publish report on website. - Purchase and install Lifebuoy at pond - complete - No progress on dredging | Lifebuoy now moved and flagpole erected. Flag purchased for St George’s Day.. |
|  | Investigate new Playground Equipment | Research | Contacted Kompan regarding a larger slide and they will site visit and give us estimates | Will seek further quotes, but, no rush on this item |
|  | Quarterly Bank Reconciliations | Adopt this policy to reconcile quarterly | To be signed by a Cllr who is not the Chair or signatory. | Q3 reconciliation done by Cllr Millar. Q4 to be done in March. |
|  | Playground Inspections | No evidence of inspections undertaken despite them happening | Clerk will investigate software to help with this as long as the relevant Cllrs agree and cost agreed | Software setup. Now need to show councillors how to use. Will arrange meeting with James Dunne of PSS |
|  | Asset Register | Review Asset Register | Noted that Asset Register should be reviewed for obsolete items and to update actual replacements costs rather than book cost. Suggested that a limit is set for assets to be added (i.e £200 if this is the excess) | Cllr Fitzpatrick will assist the clerk with this activity. Clerk to liaise with Cllr Fitzpatrick and define this. No progress. Possibly use Playground software if adopted to load assets |
|  | Accounts Exceed | Accounts exceed FSCS limit of £85000 | Council to decide whether to open additional bank accounts to ensure full cover for monies. All banking arrangements to be reviewed | Cllr Cauvain to be added although looking at the account it shows as Revoked. New Saving account now setup with Unity Bank. Funds will be transferred after Audit complete |
|  | Fencing at Spinney | Gather quotes to protect Spinney in Weeley Heath from Encroachment | Clerk to gather quotes for fencing at the Spinney | No progress – 3 quotes to be sought |
| - Fa | Facebook | To create a Read Only Facebook presence | Clerk to work with Cllr Cauvain to set this up and define a policy document | Policy amended to reflect WPC once adopted FB to be created in conjunction with Cllr Cauvain |
|  | Flagpole at Reed Pond | Research a flagpole for VE Day commemorations. | Clerk to find quotations for a Fibre Glass Flagpole of 4.6 metres to be installed ready for the VE Day commemorations of 5th May 2025. | Flagpole now installed by Cllr Spong and flags will now be flown on respective occasions |
|  | Playing Field | Look into changing policy of hiring field for commercial enterprises | Due to more commercial type hiring request it should be that the Parish Council can charge for these types of field use. | Look into changing policy and charging for commercial uses of the field. Different charging for different sizes of field use. No progress |
|  | Memorial Bench | Get quotes for a Memorial Bench | WPC has agreed to buy and install a memorial bench for Mike Brown. Clerk looking into prices and options | Options presented for approval at April Meeting |