Weeley Parish Council

Clerks Report – 19th January 2026

|  | Topic | Action/issue | Information | Status |
| --- | --- | --- | --- | --- |
|  | Weeley bypass | Determine options for the avenue of poplars | The Clerk has agreed to contact ECC Place Services to chase for a firm proposal including numbers and species of trees to plant. | Email received from ECC Place Services with suggestions. Postponing until March meeting as December meeting is very busy currently. Sourcing costs for 2 different colour Acer Trees to plant in Autumn 13/10 – On October agenda 17/11 – Postponed by Cllr Green until December 15/12 – Cllr Green to purchase trees under £7000 budget |
|  | Reed Pond | Initiate Management Plan | - Obtain costs to install a chlorine pump - Publish report on website. - Purchase and install Lifebuoy at pond – complete - No progress on dredging | Lifebuoy now moved and flagpole erected. Flag purchased for St George’s Day.. Reed Pond to be discussed at July Meeting Speaking to Kevin Green re work on the pond / Getting 3 quotes for next meeting 13/10 – Have second quote now but will move to later agenda as work will not start until next Spring now. Anonymous donation of £5000 received |
|  | Investigate new Playground Equipment | Research | Contacted Kompan regarding a larger slide and they will site visit and give us estimates | Will seek further quotes, but, no rush on this item. 16/7 – Possible use of funds for paths and surfacing 29/7 – to get quotes for surfacing 10/9 – One quote for surfacing received but waiting on Playdale visit and ROSPA report 13/10 – Report received deciding on next steps |
|  | Quarterly Bank Reconciliations | Adopt this policy to reconcile quarterly | To be signed by a Cllr who is not the Chair or signatory. | 29/7 – Bank reconciliation have a £40 discrepancy so working on this to reconcile. 11/8 – Completed by Cllr Millar and reconciled 20/10 – 2nd Quarter to be done 11/11 – Clerk and Cllr Millar currently working on this |
|  | Playground Inspections | No evidence of inspections undertaken despite them happening | Clerk will investigate software to help with this as long as the relevant Cllrs agree and cost agreed | Software setup. Now need to show councillors how to use. Will arrange meeting with James Dunne of PSS Arranging meeting with new rep. 10/9 – Arranged for ROSPA to do a 6 monthly inspection 13/10 – ROSPA report received all assets now added and Cllr Millar trained. Bi-weekly inspections due to start 15/12 – Playground Inspections now added to agenda |
|  | Asset Register | Review Asset Register | Noted that Asset Register should be reviewed for obsolete items and to update actual replacements costs rather than book cost. Suggested that a limit is set for assets to be added (i.e £200 if this is the excess) | Cllr Fitzpatrick will assist the clerk with this activity. Clerk to liaise with Cllr Fitzpatrick and define this. No progress. Possibly use Playground software if adopted to load assets 8/12 – Updating and consolidating |
|  | Cloud Storage | Find Cloud Storage for Council documents | Currently the Laptop is backed up to a memory card. As part of our risk assessment we should also back everything up to the cloud. This should enable document sharing. | 4/9 – Renewed Microsoft subscription which gives 1gb of storage for each of the 6 available accounts. I will begin to look at uploading most recent docs and making accessible to all. 13/11 – No progress |
|  | Playground Surfacing | Possible upgrade of surfacing in Over 8’s play area | Playground Surface is already coming up and therefore we may wish to use S106 monies to improve the surface. | 5/9 – One quote received. Speaking to Playdale and possibly put in a complaint to the API. 13/11 – No progress |
|  | Precept | Submit request for precept to TDC | Council agreed precept needs to be sent to TDC for approval and then payment in 2026-27 | 15/12 – Budget and precept agreed. Sent to TDC and now awaiting reply |
|  | Councillor Vacancy | Death of serving Councillor | Contact TDC Election Department and publish notices. If no election called then co-opt a new Councillor | 6/1/26 – Notices published on 29/12/25. Election period finishes on 20/1/26. If no election called then co-option at February meeting. I have had 3 interested parties so far and will inform them of the process. |
|  | TPOs | Keep a list of all trees in the area with TPOs | Using TDC and Richard Ransom records collate a list of all trees within Weeley that have current TPOs listed | 6/1/26 – process started |
|  | Weeley Parish Map | Create and publish a map showing Weeley boundaries | Map to show the outer boundaries of Weeley Paris | 12/1/26 – Map created and published |
|  | Assertion 10 | New portion added to the AGAR for 2026 | To learn about Assertion 10 and ensure Weeley is compliant |  |