Weeley Parish Council

Clerks Report – 19th May 2025

|  | Topic | Action/issue | Information | Status |
| --- | --- | --- | --- | --- |
|  | Scout Hut | Prepare a new lease. | Have initiated a chat with a new solicitor from Sparlings and have sent a copy of the lease to them. Awaiting response before contacting the Scouts. It is proposed to make the lease 35 years. Estimate received for creating a new lease but also with some information for the Scouts to be passed onto them. Scouts have now appointed representation. | Met with the Scouts along with Cllr Hamilton and have made the final statements known to our solicitor and hopefully this will now complete very soon. Chased our Solicitor for an update |
|  | Weeley bypass | Determine options for the avenue of poplars | The Clerk has agreed to contact ECC Place Services to chase for a firm proposal including numbers and species of trees to plant. | Email received from ECC Place Services with suggestions. Postponing until March meeting as December meeting is very busy currently. Sourcing costs for 2 different colour Acer Trees to plant in Autumn |
|  | Reed Pond | Initiate Management Plan | - Obtain costs to install a chlorine pump - Publish report on website. - Purchase and install Lifebuoy at pond - complete - No progress on dredging | Lifebuoy now moved and flagpole erected. Flag purchased for St George’s Day.. |
|  | Investigate new Playground Equipment | Research | Contacted Kompan regarding a larger slide and they will site visit and give us estimates | Will seek further quotes, but, no rush on this item |
|  | Quarterly Bank Reconciliations | Adopt this policy to reconcile quarterly | To be signed by a Cllr who is not the Chair or signatory. | Q3 reconciliation done by Cllr Millar. Q4 to be done in March. As per auditor will amend how we do Bank Recs |
|  | Playground Inspections | No evidence of inspections undertaken despite them happening | Clerk will investigate software to help with this as long as the relevant Cllrs agree and cost agreed | Software setup. Now need to show councillors how to use. Will arrange meeting with James Dunne of PSS Arranging meeting with new rep. |
|  | Asset Register | Review Asset Register | Noted that Asset Register should be reviewed for obsolete items and to update actual replacements costs rather than book cost. Suggested that a limit is set for assets to be added (i.e £200 if this is the excess) | Cllr Fitzpatrick will assist the clerk with this activity. Clerk to liaise with Cllr Fitzpatrick and define this. No progress. Possibly use Playground software if adopted to load assets |
|  | Accounts Exceed | Accounts exceed FSCS limit of £85000 | Council to decide whether to open additional bank accounts to ensure full cover for monies. All banking arrangements to be reviewed | Cllr Cauvain to be added although looking at the account it shows as Revoked. New Saving account now setup with Unity Bank. Funds will be transferred after Audit complete £85000 now transferred to Unity Bank Savings Account |
|  | Fencing at Spinney | Gather quotes to protect Spinney in Weeley Heath from Encroachment | Clerk to gather quotes for fencing at the Spinney | No progress – 3 quotes to be sought. Still awaiting 2 further quotes. |
| - Fa | Facebook | To create a Read Only Facebook presence | Clerk to work with Cllr Cauvain to set this up and define a policy document | Policy amended to reflect WPC once adopted FB to be created in conjunction with Cllr Cauvain. Facebook page to be created |
|  | Playing Field | Look into changing policy of hiring field for commercial enterprises | Due to more commercial type hiring request it should be that the Parish Council can charge for these types of field use. | Look into changing policy and charging for commercial uses of the field. Different charging for different sizes of field use. No progress |
|  | Memorial Bench | Get quotes for a Memorial Bench | WPC has agreed to buy and install a memorial bench for Mike Brown. Clerk looking into prices and options | Options presented for approval at April Meeting Bench ordered and to be delivered in June. |