Weeley Parish Council

Clerks Report – 16th June 2025

|  | Topic | Action/issue | Information | Status |
| --- | --- | --- | --- | --- |
|  | Scout Hut | Prepare a new lease. | Have initiated a chat with a new solicitor from Sparlings and have sent a copy of the lease to them. Awaiting response before contacting the Scouts. It is proposed to make the lease 35 years. Estimate received for creating a new lease but also with some information for the Scouts to be passed onto them. Scouts have now appointed representation. | Met with the Scouts along with Cllr Hamilton and have made the final statements known to our solicitor and hopefully this will now complete very soon. Chased our Solicitor for an update 2/6 – Now with the Scout Association. Should not be long |
|  | Weeley bypass | Determine options for the avenue of poplars | The Clerk has agreed to contact ECC Place Services to chase for a firm proposal including numbers and species of trees to plant. | Email received from ECC Place Services with suggestions. Postponing until March meeting as December meeting is very busy currently. Sourcing costs for 2 different colour Acer Trees to plant in Autumn 28th May – Emailed Essex Forest Initiative to see if any grant money available |
|  | Reed Pond | Initiate Management Plan | - Obtain costs to install a chlorine pump - Publish report on website. - Purchase and install Lifebuoy at pond - complete - No progress on dredging | Lifebuoy now moved and flagpole erected. Flag purchased for St George’s Day.. |
|  | Investigate new Playground Equipment | Research | Contacted Kompan regarding a larger slide and they will site visit and give us estimates | Will seek further quotes, but, no rush on this item |
|  | Quarterly Bank Reconciliations | Adopt this policy to reconcile quarterly | To be signed by a Cllr who is not the Chair or signatory. | Q3 reconciliation done by Cllr Millar. Q4 to be done in March. As per auditor will amend how we do Bank Recs |
|  | Playground Inspections | No evidence of inspections undertaken despite them happening | Clerk will investigate software to help with this as long as the relevant Cllrs agree and cost agreed | Software setup. Now need to show councillors how to use. Will arrange meeting with James Dunne of PSS Arranging meeting with new rep. |
|  | Asset Register | Review Asset Register | Noted that Asset Register should be reviewed for obsolete items and to update actual replacements costs rather than book cost. Suggested that a limit is set for assets to be added (i.e £200 if this is the excess) | Cllr Fitzpatrick will assist the clerk with this activity. Clerk to liaise with Cllr Fitzpatrick and define this. No progress. Possibly use Playground software if adopted to load assets |
|  | Fencing at Spinney | Gather quotes to protect Spinney in Weeley Heath from Encroachment | Clerk to gather quotes for fencing at the Spinney | No progress – 3 quotes to be sought. Reviewing quotes for next meeting (June) |
| - Fa | Facebook | To create a Read Only Facebook presence | Clerk to work with Cllr Cauvain to set this up and define a policy document | Policy amended to reflect WPC once adopted FB to be created in conjunction with Cllr Cauvain. Facebook page to be created |
|  | Playing Field | Look into changing policy of hiring field for commercial enterprises | Due to more commercial type hiring request it should be that the Parish Council can charge for these types of field use. | Look into changing policy and charging for commercial uses of the field. Different charging for different sizes of field use. No progress |
|  | Memorial Bench | Get quotes for a Memorial Bench | WPC has agreed to buy and install a memorial bench for Mike Brown. Clerk looking into prices and options | Options presented for approval at April Meeting Bench ordered and to be delivered in July. Finance to be approved at June meeting |
|  | Defib Pads Expired | Order new pads and install | Defib pad notification received from The Circuit so a new set needs to be ordered as they only last for 2 years. We will order a new set this time next year so that we always have an in date set of pads. | Ordered a set of pads and paid for them directly with Debit Card. Diary entry for this time next year to order another set. On Finance list for June |
|  | External Audit | Prepare and send off External Audit Requirements | Each year we must comply with External Audit procedures and complete an AGAR and the other relevant documents. | Forms completed and sent to PKF Littlejohn, but, as our expenditure last year was greater than £200000 we now need to provide extra documents as an Intermediate Council. This is just for this year. |
|  | Petanque Sign | Design sign as per Petanque request | The Petanque court has been used recently by other ball sports so they have requested a sign to discourage this. | Sign researched and cost known – to be added to next Council meeting (Jun). Sing ordered Finance to be approved in June |
|  | CCTV | Replace and Upgrade Existing CCTV. Install a Camera on our Lamppost by the Station Approach | CCTV is aging and could do with an upgrade around the hall to cover more of the area in better quality. Also where there is consistent Fly Tipping on Station Approach it would be pertinent to install a camera. | One quote received. Clerk to source further quotes. 4/6/25 – requested 2 further quotes On June agenda but only one quote received so far. |