Weeley Parish Council

Clerks Report – 15th Sept 2025

|  | Topic | Action/issue | Information | Status |
| --- | --- | --- | --- | --- |
|  | Scout Hut | Prepare a new lease. | Have initiated a chat with a new solicitor from Sparlings and have sent a copy of the lease to them. Awaiting response before contacting the Scouts. It is proposed to make the lease 35 years. Estimate received for creating a new lease but also with some information for the Scouts to be passed onto them. Scouts have now appointed representation. | Met with the Scouts along with Cllr Hamilton and have made the final statements known to our solicitor and hopefully this will now complete very soon. Chased our Solicitor for an update 2/6 – Now with the Scout Association. Should not be long 16/7 – In receipt of lease to be signed at 21st July meeting 29/7 – Lease returned to Solicitor awaiting Scouts sign off 10/9 – Scouts completed their side just awaiting final bill from our Solicitor now |
|  | Weeley bypass | Determine options for the avenue of poplars | The Clerk has agreed to contact ECC Place Services to chase for a firm proposal including numbers and species of trees to plant. | Email received from ECC Place Services with suggestions. Postponing until March meeting as December meeting is very busy currently. Sourcing costs for 2 different colour Acer Trees to plant in Autumn 28th May – Emailed Essex Forest Initiative to see if any grant money available. No news on grants, but Kevin G has some thoughts on trees we will follow up in Autumn. Pick up again in October |
|  | Reed Pond | Initiate Management Plan | - Obtain costs to install a chlorine pump - Publish report on website. - Purchase and install Lifebuoy at pond – complete - No progress on dredging | Lifebuoy now moved and flagpole erected. Flag purchased for St George’s Day.. Reed Pond to be discussed at July Meeting Speaking to Kevin Green re work on the pond / Getting 3 quotes for next meeting 10/9 – Suggestion of using back left of pond for excavated silt. 1 quote received hoping to have one or two more for Sept meeting |
|  | Investigate new Playground Equipment | Research | Contacted Kompan regarding a larger slide and they will site visit and give us estimates | Will seek further quotes, but, no rush on this item. 16/7 – Possible use of funds for paths and surfacing 29/7 – to get quotes for surfacing 10/9 – One quote for surfacing received but waiting on Playdale visit and ROSPA report |
|  | Quarterly Bank Reconciliations | Adopt this policy to reconcile quarterly | To be signed by a Cllr who is not the Chair or signatory. | Q3 reconciliation done by Cllr Millar. Q4 to be done in March. 29/7 – Bank reconciliation have a £40 discrepancy so working on this to reconcile. 11/8 – Completed by Cllr Millar and reconciled |
|  | Playground Inspections | No evidence of inspections undertaken despite them happening | Clerk will investigate software to help with this as long as the relevant Cllrs agree and cost agreed | Software setup. Now need to show councillors how to use. Will arrange meeting with James Dunne of PSS Arranging meeting with new rep. 10/9 – Arranged for ROSPA to do a 6 monthly inspection |
|  | Asset Register | Review Asset Register | Noted that Asset Register should be reviewed for obsolete items and to update actual replacements costs rather than book cost. Suggested that a limit is set for assets to be added (i.e £200 if this is the excess) | Cllr Fitzpatrick will assist the clerk with this activity. Clerk to liaise with Cllr Fitzpatrick and define this. No progress. Possibly use Playground software if adopted to load assets |
|  | Fencing at Spinney | Gather quotes to protect Spinney in Weeley Heath from Encroachment | Clerk to gather quotes for fencing at the Spinney | No progress – 3 quotes to be sought. Reviewing quotes for next meeting (June) 16/7 – Quote accepted in June and work to start ASAP – the fencing along the front will be below the 3ft or 1 metre Planning rules. 29/7 work started by chosen supplier 10/9 – Work completed and payment to be made this month |
|  | Playing Field | Look into changing policy of hiring field for commercial enterprises | Due to more commercial type hiring request it should be that the Parish Council can charge for these types of field use. | Look into changing policy and charging for commercial uses of the field. Different charging for different sizes of field use. No progress 15/9 – New Playground Hire policy and terms and conditions to be agreed at September meeting |
|  | Memorial Bench | Get quotes for a Memorial Bench | WPC has agreed to buy and install a memorial bench for Mike Brown. Clerk looking into prices and options | Options presented for approval at April Meeting Bench ordered and to be delivered in July. Finance to be approved at June meeting 16/7 – Bench delivered and decide on location at July meeting 10/9 – Decide at meeting on Monday 15th September |
|  | External Audit | Prepare and send off External Audit Requirements | Mandatory External Audit of year to 31st March 2025. Submit AGAR documents to PKF Littlejohn as requested. Display on Website and Noticeboards On successful conclusion of audit publish on Website and Noticeboards | Forms completed and sent to PKF Littlejohn, but, as our expenditure last year was greater than £200000 we now need to provide extra documents as an Intermediate Council. This is just for this year. 16/7 – Awaiting response from External Audit 29/7 – Received response from auditor and sent further documents as requested. 10/9 – Audit complete and passed – documents published as needed |
|  | CCTV | Replace and Upgrade Existing CCTV. Install a Camera on our Lamppost by the Station Approach | CCTV is aging and could do with an upgrade around the hall to cover more of the area in better quality. Also where there is consistent Fly Tipping on Station Approach it would be pertinent to install a camera. | One quote received. Clerk to source further quotes. 4/6/25 – requested 2 further quotes On June agenda but only one quote received so far. 16/7 - Postponed again 29/7 – will request further quotes as per Financial Regs 11/8 – Contacted Frinton Alarm Systems Ltd 10/9 – 2 quotes to be presented at Sept Meeting |
|  | Cloud Storage | Find Cloud Storage for Council documents | Currently the Laptop is backed up to a memory card. As part of our risk assessment we should also back everything up to the cloud. This should enable document sharing. | 4/9 – Renewed Microsoft subscription which gives 1gb of storage for each of the 6 available accounts. I will begin to look at uploading most recent docs and making accessible to all. |
|  | Playground Surfacing | Possible upgrade of surfacing in Over 8’s play area | Playground Surface is already coming up and therefore we may wish to use S106 monies to improve the surface. | 5/9 – One quote received. Speaking to Playdale and possibly put in a complaint to the API. |