Weeley Parish Council

Clerks Report – 20th October 2025

|  | Topic | Action/issue | Information | Status |
| --- | --- | --- | --- | --- |
|  | Scout Hut | Prepare a new lease. | Have initiated a chat with a new solicitor from Sparlings and have sent a copy of the lease to them. Awaiting response before contacting the Scouts. It is proposed to make the lease 35 years. Estimate received for creating a new lease but also with some information for the Scouts to be passed onto them. Scouts have now appointed representation. | Met with the Scouts along with Cllr Hamilton and have made the final statements known to our solicitor and hopefully this will now complete very soon. Chased our Solicitor for an update 10/9 – Scouts completed their side just awaiting final bill from our Solicitor now 13/10 – Still waiting |
|  | Weeley bypass | Determine options for the avenue of poplars | The Clerk has agreed to contact ECC Place Services to chase for a firm proposal including numbers and species of trees to plant. | Email received from ECC Place Services with suggestions. Postponing until March meeting as December meeting is very busy currently. Sourcing costs for 2 different colour Acer Trees to plant in Autumn 13/10 – On October agenda |
|  | Reed Pond | Initiate Management Plan | - Obtain costs to install a chlorine pump - Publish report on website. - Purchase and install Lifebuoy at pond – complete - No progress on dredging | Lifebuoy now moved and flagpole erected. Flag purchased for St George’s Day.. Reed Pond to be discussed at July Meeting Speaking to Kevin Green re work on the pond / Getting 3 quotes for next meeting 13/10 – Have second quote now but will move to later agenda as work will not start until next Spring now. Anonymous donation of £5000 received |
|  | Investigate new Playground Equipment | Research | Contacted Kompan regarding a larger slide and they will site visit and give us estimates | Will seek further quotes, but, no rush on this item. 16/7 – Possible use of funds for paths and surfacing 29/7 – to get quotes for surfacing 10/9 – One quote for surfacing received but waiting on Playdale visit and ROSPA report 13/10 – Report received deciding on next steps |
|  | Quarterly Bank Reconciliations | Adopt this policy to reconcile quarterly | To be signed by a Cllr who is not the Chair or signatory. | Q3 reconciliation done by Cllr Millar. Q4 to be done in March. 29/7 – Bank reconciliation have a £40 discrepancy so working on this to reconcile. 11/8 – Completed by Cllr Millar and reconciled 20/10 – 2nd Quarter to be done |
|  | Playground Inspections | No evidence of inspections undertaken despite them happening | Clerk will investigate software to help with this as long as the relevant Cllrs agree and cost agreed | Software setup. Now need to show councillors how to use. Will arrange meeting with James Dunne of PSS Arranging meeting with new rep. 10/9 – Arranged for ROSPA to do a 6 monthly inspection 13/10 – ROSPA report received all assets now added and Cllr Millar trained. Bi-weekly inspections due to start |
|  | Asset Register | Review Asset Register | Noted that Asset Register should be reviewed for obsolete items and to update actual replacements costs rather than book cost. Suggested that a limit is set for assets to be added (i.e £200 if this is the excess) | Cllr Fitzpatrick will assist the clerk with this activity. Clerk to liaise with Cllr Fitzpatrick and define this. No progress. Possibly use Playground software if adopted to load assets |
|  | Playing Field | Look into changing policy of hiring field for commercial enterprises | Due to more commercial type hiring request it should be that the Parish Council can charge for these types of field use. | Look into changing policy and charging for commercial uses of the field. Different charging for different sizes of field use. No progress 15/9 – New Playground Hire policy and terms and conditions to be agreed at September meeting 13/10 – Agreed and adopted at September meeting |
|  | Memorial Bench | Get quotes for a Memorial Bench | WPC has agreed to buy and install a memorial bench for Mike Brown. Clerk looking into prices and options | Options presented for approval at April Meeting Bench ordered and to be delivered in July. Finance to be approved at June meeting 13/10 – Bench now in place |
|  | CCTV | Replace and Upgrade Existing CCTV. Install a Camera on our Lamppost by the Station Approach | CCTV is aging and could do with an upgrade around the hall to cover more of the area in better quality. Also where there is consistent Fly Tipping on Station Approach it would be pertinent to install a camera. | One quote received. Clerk to source further quotes. 11/8 – Contacted Frinton Alarm Systems Ltd 10/9 – 2 quotes to be presented at Sept Meeting 13/10 – Quote agreed and CCTV upgraded and installed on 9th October |
|  | Cloud Storage | Find Cloud Storage for Council documents | Currently the Laptop is backed up to a memory card. As part of our risk assessment we should also back everything up to the cloud. This should enable document sharing. | 4/9 – Renewed Microsoft subscription which gives 1gb of storage for each of the 6 available accounts. I will begin to look at uploading most recent docs and making accessible to all. 13/10 – No progress |
|  | Playground Surfacing | Possible upgrade of surfacing in Over 8’s play area | Playground Surface is already coming up and therefore we may wish to use S106 monies to improve the surface. | 5/9 – One quote received. Speaking to Playdale and possibly put in a complaint to the API. 13/10 – No progress |
|  | Play ground signs | Signs needed in playground as per ROSPA recommendation | Signs to be sourced and then installed | !3/10 – Signs purchased and received now need installation. |