Weeley Parish Council

Clerks Report – 15th June 2026

|  | Topic | Action/issue | Information | Status |
| --- | --- | --- | --- | --- |
|  | Reed Pond | Initiate Management Plan | - Obtain costs to install a chlorine pump - Publish report on website. - Purchase and install Lifebuoy at pond – complete - No progress on dredging | Lifebuoy now moved and flagpole erected. Flag purchased for St George’s Day.. Reed Pond to be discussed at July Meeting Speaking to Kevin Green re work on the pond / Getting 3 quotes for next meeting 13/10 – Have second quote now but will move to later agenda as work will not start until next Spring now. Anonymous donation of £5000 received 10/2/26 – On Feb Agenda 23/2/26 – Contractor chosen just waiting for the work to start |
|  | Investigate new Playground Equipment | Research | Contacted Kompan regarding a larger slide and they will site visit and give us estimates | Will seek further quotes, but, no rush on this item. 16/7 – Possible use of funds for paths and surfacing 29/7 – to get quotes for surfacing 10/9 – One quote for surfacing received but waiting on Playdale visit and ROSPA report 13/10 – Report received deciding on next steps 16/4 – Looking into safer surfacing for the area of uneven turf. One quote received and a further one being researched. 18/5 -Attempting to get one final quote 8/6 – On June Agenda |
|  | Quarterly Bank Reconciliations | Adopt this policy to reconcile quarterly | To be signed by a Cllr who is not the Chair or signatory. | 29/7 – Bank reconciliation have a £40 discrepancy so working on this to reconcile. 11/8 – Completed by Cllr Millar and reconciled 20/10 – 2nd Quarter to be done 11/11 – Clerk and Cllr Millar currently working on this 23/2 – Q1,2 and 3 completed 16/4 – Q4 to be dome this month 30/4 – Q4 done and audited |
|  | Cloud Storage | Find Cloud Storage for Council documents | Currently the Laptop is backed up to a memory card. As part of our risk assessment we should also back everything up to the cloud. This should enable document sharing. | 4/9 – Renewed Microsoft subscription which gives 1gb of storage for each of the 6 available accounts. I will begin to look at uploading most recent docs and making accessible to all. 13/11 – No progress |
|  | TPOs | Keep a list of all trees in the area with TPOs | Using TDC and Richard Ransom records collate a list of all trees within Weeley that have current TPOs listed | 6/1/26 – process started |
|  | Assertion 10 | New portion added to the AGAR for 2026 | To learn about Assertion 10 and ensure Weeley is compliant | 15/2 – Report run against Website and to be studied. Already have gov.uk accounts |
|  | 9.25/5 | Finger Post at Crow Lane | Is this listed or should it be listed. Can we just clean it or replace it. Who owns it | 22/1/26 – Clerk emailed highways Essex to clarify who owns the finger post and TDC to see if it is on a Local Heritage List 10/3- Chased Open Spaces for their permission 13/3 – Permission granted to replace – discuss on March agenda 9/4/26 – No progress |
|  | 9.25/6 | Flashing Speed Signs | Possibility of installing some of these in Weeley | 22/1/26 – Clerk emailed Cllr D Land to discuss |
|  | 10/26.8 | Plaque request from WIB | Weeley in Bloom would like to place a plaque on the bench by the Fire Station in honour of a member who used to maintain this area | 19/1 – Council voted to allow plaque 22/1 – Clerk notified WiB of permission 24/2 – Just awaiting confirmation from WIB of lettering 8/6 – Plaque seen now to arrange install |
|  | 11.26/8 | Barleyfields lighting | Contact Rose and discuss the options for lighting removal | 27/2 – Spoken to Rose and sent them a Letter of Authority to speak to UK Power Networks to see what can be done with our lights. 18/5 – No update 8/6 – Chased Rose – no updates |
|  | Defibrillator Theft | Defibrillator Stolen and needs to be replaced | Report to police and insurance and then research a new Case and Defibrillator. | 20/4 – Reported to the Police 23/4 – reported to Insurance awaiting response 8/6 – Videos sent to Insurance awaiting response |
|  | Policies / ACM 6/ 02.26.9 | Policies | Policies adopted at meeting to be added to website | 1/6 – All policies added to website |
| - C | Budgens | Issues for residents around 7 Colchester Road | Communicate between residents and TDC regarding ongoing issues at Colchester Road | 1/6 – Raised further issues with the Planning dept at TDC |
|  | 02.26/11 | Goalmouths and Hedge along Old Clacton Road | Previous goal mouths need restoring and the hedge along the road needs cutting back to allow cars to park there | 18/5 – Council agreed to Goldacre doing the work 1/6 – Advised Goldacre to do the work but hedge cutting will wait until nesting season over |